2025 Maplewoodstock Music and Arts Festival

Township Department Heads Meeting Agenda

Introductions

Administration

- Event application submitted

- Social Affairs permit received

- Insurance obtained and COI submitted to township

DPW

- Dumpsters – same as last year

- Trash and recycling receptacles

  - We would like additional recycling bins

- Light towers:  How many may be available?    How  can we request / do we need to obtain extras?

- Access to electrical boxes on Oakview and backstage

- Set up

  - Stage will arrive Friday morning

  - Stakes for walking lanes

  - Snow fencing behind the stage

  - Snow fencing for the beer garden

  - Snow fencing for the 60/90 baseball field

  - Snow fencing around one tree in park

  - Note:  Working with Conservancy for other tree protection

Police / Security

- Proposed security attached – requesting quote and discuss traffic

- Propose Oakview one-way from Dunnell to Valley

- Dunnell and Baker (from Dunnell to Valley) have parking reserved for vendors, bands & volunteers – could we use cones and signs to mark parking, in addition to sawhorses

- Emergency egress lanes and barriers in front of stage

EMS / SORS: rig, cooling tent and personnel on site – could we request for generator from DPW

Food Vendor Permits

Sensory activation area – same as last year; SAV provided by South Orange and being delivered Friday

Maplewoodstock 2025 Map

Tents

Long Hall Tent: 30x60 – permit awarded

Beer Garden

- Three  20x40 tents

- Three  10x20 tents

Sensory Activation Area: 10x20 pop up tent

Merchandise Tent: 10x20 pop up tent

Sponsor Tent along front of field between stage and Oakview: 10x20 pop up tent

Backstage

- 10x10 frame tent with sides

- 10x 20 pop up tent

- Two 10x10 pop up tents

Misting Tent at top of hill, across from train station: 10x20 pop up tent

Maplewoodstock 2025 – Proposed Security Needs

|  | Saturday | Sunday |
| --- | --- | --- |
| Beer Garden 1 officer | Noon to 9pm | Noon to 9pm |
| Kid Zone / Hill Field 1 officer | Noon to 9pm | Noon to 9pm |
| Stage Security 1 officer 2 officers (from Beer / Kid) | 4pm to 11pm 9pm – 11pm | 4pm to 11pm 9pm – 11pm |
| General Event Security 3 officers (1 East Field, 2 Hill Field) 5 officers (1 East Field, 4 Hill Field) | 2pm – 5pm 5pm – 11pm | 2pm – 5pm 5pm – 11pm |
| Traffic 2 officers – 1 at Valley & Oakview & 1 at Dunnell & Oakview | 10am thru 11pm | 10am thru 11pm |