MAPLEWOODSTOCK VOLUNTEER COMMITTEE

MEETING NOTES – April 12, 2023

Items to be discussed

Band Selections and Headliners (Tarquin/Jamie)

- Band lineup is completed (attached)

- Emails went out to selected bands. They have until next Tuesday to confirm
(Gary, I will send you the line-up with the band bios in a few days – this may be subject to change if bands drop out)

- Waitlisted bands and not selected bands will get their emails in the next day or two.

- Headliners are:

  - Red Baraat followed by Mihali on Saturday

  - Remember Jones followed by Louis Cato Band on Sunday

- Al Gold and Qtip bandits will be back! Jamie to call Qtip Bandits

- 35-38% were local bands.  Some were extraordinary - high number. Will communicate to the bands selected, not and waitlisted.  Jamie made a ranking system that worked well.

- We should ask local bands how many times they have applied / played in the application process.

- 5-6 bands who are local and have applied a bunch of times are on the waitlist.

- Good mix of diversity and style of bands and ages of players - need some info for the press release

- Do a commemorative thing for Jim Buchanan before band plays

- Targeting April 30 for press release

- All in: 12+7+6+12 = 37k

- TL to rewrite all the bios

Advertising update (Gary)

- $$ Update we are at about $49k!

- Program status -

  - Charlie is starting to work on program.

  - Needs 2 weeks to assemble. Has all advertsing, tshirt designs.

  - Page for some vendors, the map to hype vendors

  - TL needs to rewrite bios to fit / Jim will help - the managers have to approve.

  - David Worral needs two weeks for print

  - Have to pick up programs on May 19 for Mayfest.

  - TL will get headliner write up to Gary by the 18th

  - Jim will make the list of the other bands

  - TL to provide names of brewers to be in Beer Garden

  - note about tshirt design - TL to provide wording

Merch update (Jamie)

- Time-line for delivery

  - Colors and styles reasonably in stock.  Need 3 weeks. Expect to have order in at the end of this week

  - planning 850

  - balancing colors and options

- Designs

  - Swallows with maple leaves

  - Art Nouveau poster

  - possible third design - maybe for kids

- NEED LAWN SIGNS

- Susan send Jamie and Tarquin the prior year price list

- Susan ask for old lawn signs

- Discuss dates to sell - Mayfest, Duck Races and some Saturdays

- Discuss getting volunteers

  - Form on website - Katie has access

  - Possibly bring in Mark Slade and Mark Loughney to help. They both continue to talk about their interest to get more involved. Just a thought.

Vendor and Kids Zone update (Katie)

Park layout – anything to discuss?? (Katie)

- Beer Garden is basically same area; can adjust slightly

- Gary will share the one Katie provided / shared in the meeting

- Need slightly tighter map for program / easier to read

- Compass, DCH Audi, Mark Slade will have the front row tents

- Senior tent location decision

Beer Garden update (Tarquin)

- Status

  - 3 local brewers / put names in program

  - Elks to have meeting this week

  - May need a deposit

- Music/sound options

  - Do we have live music that we control, or should we let Elks control? Do we pay for a feed from the stage?

  - Music in beer garden - want to get festival sound into beer graden / do not want counter programming.  Speaker stack on the otherside of the creek.  Wifi or hard wired

  - Matt proposed 2-5pm acoustic, they choose the music/bands and bring in the music

  - Try getting sound there this year and if we cannot then a new plan for 2024

  - Include a box of brochures and possibly a large board with the band timeslots

Gaming permit for 50/50 (Brad)

- We  can get a permit; Brad will apply

- Canopy volunteers to coordinate selling during festival - focus on a few timeslots

- Announce winner before headliner

Any Canopy lottery items to discuss at this time? (Brad)

- Need to layout spots on Friday morning.

- Working with HS kids on the program to draw / manage winners

- Biggest change is that the entry period is open for 10 days  and will end a week before MWS to get people focused

- Advertise it is coming for 2-3 weeks before the window opens

- FAQs etc ready to go for website

Other items

- Need a new 501c3; does not need immediate decision.

- Review timelines and items that need to get done before May

- town meetings?

- Port a potty cleaning…

- Press release plan needed

  - band stats

  - Mahali is local guy

  - layout reference

  - beer garden

Jill Crisciulo invoked at 8:39pm