Maplewoodstock 2025

Meeting Follow-Ups								March 13, 2025

| What | Who | When |
| --- | --- | --- |
| Pull all possible tshirt art files | Jamie | March 24 |
| Determine if we can make a poster of the designs | Anyone? |  |
| Reach out to Rick for other sounds ideas for East Field and other lighting ideas for the hill | Susan | March 17 |
| Find out how we can get a banner over Maplewood Ave and Springfield | Susan | April 1 |
| Meet with graphic designer | Jim Jamie Others? | March 17 or 18 |
| Review tshirt designs | All | March 28 |
| Final tshirt design |  | April 4 |
| Revise East field layout | Brad & Jim | April 4 |
| Create general map for the program | Brad & Jim | April 5 |
| Provide Gary with a photography retrospective of 20 years | Jamie | March 31 |
| Provide Gary with a feature article of the 20 under 20 art installation | Amy | March 31 |
| Provide Gary with a list of donor names | Brad | April 4 |
| Band Committee Meeting | Band Committee | March 27 |
| Band Committee decisions | Band Committee | April 2 |
| Band Line up drafted | Band Committee | April 5 |
| Send letters to accepted and waitlisted bands | Susan | April 6 |
| Layout line up pages | WHO? | April 8 |
| Review program with committee | Gary | April 9 or 10 |
| Bands must reply |  | April 13 |
| Final program to Charlie | Gary | April 18 |
| Send letters to rejected bands | Susan | April 18 |