| Who | Tarquin | Jamie | Kevin | Gary | Jim | Brad | Susan | Brian | Others |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Sponsors / Ads/ Additional Fundraising - Solicit sponsors - Collect artwork - Program |  |  |  | primary |  | Help with new sponsors |  |  |  |
| Music - Headliners - Local - Production Company lead | primary | On cmte | On cmte | On cmte |  |  |  |  |  |
| Craft / Art / General Vendors - Identification / recruitment - Selection - Layout within - Setup, onsite management, load out |  | To discuss with Brian |  |  |  |  |  | primary |  |
| Food Vendors - Identification / recruitment - Selection - Layout within - Setup, onsite management, load out |  |  | primary |  |  |  |  |  |  |
| Beer Garden / Elks Partnership - Engage Elks - Work with Elks on beers and prices - Coordinate set up, etc | primary |  |  | assist |  | Handle finances |  |  |  |
| Kid Zone - Identification / recruitment - Selection - Layout within - Setup, onsite management, load out |  | Pull Adam’s contact info |  |  |  |  |  |  | Would Adam do it? |
| Park Aesthetics: design, source, install, maintain: - Lights - Signage - Overall décor - Backstage set up - Port a potties |  |  |  |  | Jim to ask Amy to play a strong role |  |  |  | Would Danny help? |
| Art - Exhibit - Community project | assist |  |  |  | Lead ideation – need execution support |  |  |  |  |
| Canopies - Lottery and technology - Raffle/Auction - Set up |  |  |  |  |  | primary |  |  |  |
| Branded Merchandise - Design - Order - Organize selling before - Lead sales the weekend of | Take lead with Jim on design | Manage ordering |  |  | Take lead with TL on design |  | Lead sales before and during |  |  |
| Publicity / Social Media - Pre-festival promotion - Partner with others to execute their advance messages - Manage socials and promotion on-site during festival |  |  |  |  | primary |  |  |  |  |
| Partners - Together We Bloom - SO Rescue Squad - SOMA Two Towns - Other? |  |  |  |  | primary | Work with TWB also |  |  |  |
| Volunteer Management - Collect requirements - Organize sign ups - Manage weekend of |  |  |  |  |  | Rachel Goldman |  |  |  |
| Finances and Contracts - Manage the books - Contract negotiations - Insurance - Permits - Licenses |  |  |  |  |  | primary |  |  |  |
| Administration & Township Liaison - Police coordination - DPW - Manage agendas and meetings - Other |  |  |  |  |  |  | primary |  |  |

Additional resources

- Brian- Jamie to talk to Brian about leading vendors and joining committee

- Danny – Susan to talk to him about overall level of engagement

- Amy B – Jim to talk to Amy about engagement on aesthetics

- Adam – Jamie to pull his contact info.  Susan can reach out to him