Maplewoodstock 2024

August Committee Discussion Topics

Review of 2023 Festival

Financial performance

- 50/50 profit (was it worth it/needed)?

What went well

- Brad: Audio quality and production overall tremendously improved. Sound in audience sounded very good.  Production staff friendly and accommodative.

- Brad: Kid Zone on “stage side” worked well; canopies not affected.

- Brad: Music performances excellent; good variety of styles.

- Brad: Earlier Sunday night ending/cleanup

What could be better

- Brad: Need better ice solution (especially if very hot). Buying ice retail isn’t optimal.

  - Tom: Suggest having an Ice Vendor/truck on site selling ice as needed.

- Brad: Festival to purchase its own coolers, fans, etc. if $ permits.  Would make setup and cleanup easier.

- Brad: Vendor layout better but still not optimal

  - Tom: The splitting of vendors turned out not to be ideal. On Sunday some vendors actually request to be moved off of the hill and onto the east field.

- Brad: Cohesive decorations/art around festival site to improve overall vibe.

  - Tom: Potential for reaching out to the art community

- Brad: No HS kids could be found to clean bathrooms. Hire service?

  - Tom: Will need to price out options

- Brad: “College kid zone” disruptive to some

Ideas for 2024 festival improvement

- Any 2023 Surplus available for investment/new purchases?

  - Brad: Storage Unit

  - Brad: Festival coolers, fans, canopies for band checkin area

  - Brad: “Festival Merch” sign for roof of merch tent? Multiple merch tents?

  - Brad: Ferris wheel?

  - Brad: Festival layout review

  - Brad: Video screens on sides of stage/beer garden?

Spectator/band/vendor survey?

Vendors

Are vendors a must have (for financial and/or experiential reasons)

- How much money do vendors contribute to the overall budget?

If keeping the vendors…

- Identify a new committee member or does an existing committee member have interest/capacity?

- What kind of volunteer/committee member should we be seeking (industry experience)?

- Ideas of people to invite?

- Deadline for identifying new leadership

- Transition from Katie/info exchange

Township Relations

- Proactive plan to stay in front of potential regulation

- Maplewood Bible Church issue

- Generators

- Vendors

501(c)(3) Plan

- How are we going to proceed?